|  | Beccaria: 7 STEPS TO A SUCCESSFUL CRIME PREVENTION PROJECT Worksheet for Step 3: Specifying the Goals |
| --- | --- |

| ? | Which goal(s) would you like to achieve with the project? What would you like to change and effectuate precisely? Which side-goals would you like to achieve with the project? |
| --- | --- |
|  | ... |
| !. | Define a/several project goals! Specify precise (side-)goals! - high/lower importance (side-)goals - measurable/checkable (side-)goals Sort your (side-)goals according to importance!! Narrow down your (side-)goals to what is essential! |
|  | ... |
| ?. | - Is/are your (side-)goal/s realistic with regard to time, personnel and finance? - How can you later check, if you have reached your (side-)goals? - How will you recognise whether you have reached your (side-)goals? Are there measurable criteria? - What measurable criteria are there for the attainment of a (side-)goal? |
|  | ... |

| ? | - Are the (side-)goal objectives attainable in the project’s running-time? - When should a particular (side-)goal be reached by? (short-term; middle-term; long-term) |
| --- | --- |
|  | ... |
| !. ?. | Establish precisely the point in time, by when a specific (side-)goal should be achieved! Consider buffer times with your time-plan for unforeseen circumstances! (10-15%) - Where would you like to procure your financial support from?(public means, private sponsoring, third-party funds) - How should the financing of the project be carried out? - What can the project cost in total? |
|  | ... |

| ! | Make a table, regarding how much money have, and how much you need for individual tasks! |
| --- | --- |
|  | ... |
| ?. | Is the budget adequate, or rather realistic for the implementation of the goals? Can you stick to estimated project costs? |
|  | ... |
| ?. | - Are personal and material costs (pressure, forwarding expenses) etc. incorporated? - Are the costs proportionate to the targeted changes, goals? |
|  | ... |

| ? | - Can I definitely reach the target-group with my measure/s? - How many people should be reached with the measure/s? |
| --- | --- |
|  | ... |
| ?. | - Which particular characteristics does the target-group possess? Give details among other things regarding: - age - gender - location (also social) |
|  | ... |

| ? | Are there ways through which the target-group could be better reached (eg. teachers, peers etc.)? |
| --- | --- |
|  | ... |